## Dashboard
PARADIGM GSPL ENGINE
Production Readiness Tracker
Current Score | 40 | / 100
40
Category | Max Pts | Current | Target | Gap
Security & Auth | 20 | 6 | 20 | 14
Input Validation | 10 | 1 | 10 | 9
Error Handling | 10 | 3 | 10 | 7
Data Layer | 10 | 2 | 10 | 8
API Completeness | 10 | 7 | 10 | 3
Frontend Polish | 10 | 4 | 10 | 6
Testing | 10 | 5 | 10 | 5
DevOps & Deploy | 10 | 6 | 10 | 4
Documentation | 5 | 4 | 5 | 1
Observability | 5 | 2 | 5 | 3
TOTAL | 100 | 40 | 100 | 60

## Issues
ID | Issue | Category | Priority | Sprint | Status | File(s) | Fix Description
SEC-01 | No CORS middleware configured | Security & Auth | P0 | Sprint 1 | TODO | server.ts | Add cors package + app.use(cors({origin}))
SEC-02 | No HTTPS/TLS enforcement | Security & Auth | P0 | Sprint 1 | TODO | server.ts, nginx.conf | Add Helmet.js, enforce HTTPS redirect in nginx
SEC-03 | Private keys accepted in request bodies | Security & Auth | P0 | Sprint 1 | TODO | server.ts L947,1066 | Move signing client-side, accept only signed payloads
SEC-04 | /metrics endpoint is public | Security & Auth | P0 | Sprint 1 | TODO | server.ts, nginx.conf | Restrict /metrics to internal IPs or add bearer token
SEC-05 | WebSocket has no authentication | Security & Auth | P0 | Sprint 1 | TODO | server.ts L1250 | Verify JWT during WebSocket upgrade handshake
SEC-06 | JWT secret falls back to random value | Security & Auth | P1 | Sprint 1 | TODO | src/lib/auth/index.ts L13 | Throw error if JWT_SECRET missing in production
SEC-07 | No refresh token rotation | Security & Auth | P1 | Sprint 2 | TODO | src/lib/auth/index.ts | Implement short-lived access + long-lived refresh tokens
SEC-08 | No session revocation / JWT blacklist | Security & Auth | P1 | Sprint 2 | TODO | src/lib/auth/ | Add Redis-backed token blacklist for logout
SEC-09 | No role-based access control | Security & Auth | P1 | Sprint 2 | TODO | server.ts (all endpoints) | Add requireAuth + requireRole middleware, enforce on all protected routes
SEC-10 | Seed deletion has no auth check | Security & Auth | P1 | Sprint 1 | TODO | server.ts L373 | Wrap DELETE /api/seeds/:id with requireAuth + ownership
SEC-11 | Rate limiter is in-memory only | Security & Auth | P1 | Sprint 2 | TODO | server.ts L159-189 | Replace with Redis-backed sliding window
SEC-12 | No CSRF protection | Security & Auth | P2 | Sprint 3 | TODO | server.ts | Add SameSite cookies or stateless CSRF tokens
SEC-13 | MongoDB/Redis containers have no auth | Security & Auth | P2 | Sprint 2 | TODO | docker-compose.yml | Add MONGO_INITDB_ROOT_PASSWORD, redis --requirepass
SEC-14 | CSP allows unsafe-inline/unsafe-eval | Security & Auth | P2 | Sprint 3 | TODO | nginx.conf L24 | Switch to nonce-based CSP for production
SEC-15 | Blockchain RPC URL not validated | Security & Auth | P2 | Sprint 3 | TODO | src/lib/sovereignty/onchain.ts | Whitelist known Infura/Alchemy endpoints
VAL-01 | POST /api/seeds — no body validation | Input Validation | P0 | Sprint 1 | TODO | server.ts L336 | Add Zod schema: domain (enum 27), name (string max 255), genes (typed map)
VAL-02 | POST /api/seeds/generate — no schema | Input Validation | P0 | Sprint 1 | TODO | server.ts L385 | Add Zod: prompt (string max 2000), domain (enum)
VAL-03 | POST /api/seeds/:id/mutate — rate unchecked | Input Validation | P0 | Sprint 1 | TODO | server.ts L470 | Validate rate: z.number().min(0).max(1)
VAL-04 | PUT /api/seeds/:id/genes — no validation | Input Validation | P0 | Sprint 1 | TODO | server.ts L620 | Validate gene_name, gene_type (enum 17), value (type-specific)
VAL-05 | POST /api/auth/register — weak username check | Input Validation | P0 | Sprint 1 | TODO | server.ts L302 | Add: username min 3 / max 50 / alphanumeric, password min 8 + complexity
VAL-06 | POST /api/agent/query — no length limit | Input Validation | P1 | Sprint 1 | TODO | server.ts L1153 | Limit query to 5000 chars, sanitize
VAL-07 | GET /api/seeds — no pagination | Input Validation | P0 | Sprint 1 | TODO | server.ts L332 | Add ?limit=50&offset=0, enforce max=1000
VAL-08 | Frontend forms lack Zod validation | Input Validation | P1 | Sprint 2 | TODO | src/pages/AuthPage.jsx, MintPanel | Add Zod schemas for all frontend forms
VAL-09 | Ethereum address not validated in MintPanel | Input Validation | P1 | Sprint 2 | TODO | src/components/studio/MintPanel.jsx L122 | Validate 0x + 40 hex chars
VAL-10 | Gene editor vector inputs accept any number | Input Validation | P2 | Sprint 3 | TODO | src/components/studio/GeneEditor.jsx | Add per-gene-type range validation
ERR-01 | No React ErrorBoundary wrapping studio | Error Handling | P0 | Sprint 1 | TODO | src/pages/StudioPage.jsx | Add ErrorBoundary component, show recovery UI on crash
ERR-02 | No WebGL fallback in PreviewViewport | Error Handling | P0 | Sprint 1 | TODO | src/components/studio/PreviewViewport.jsx | Detect WebGL support, show message if unavailable
ERR-03 | Silent API failures — 12 console.error catches | Error Handling | P0 | Sprint 1 | TODO | All studio components | Replace console.error with toast notifications (sonner is installed)
ERR-04 | No retry logic in API client | Error Handling | P1 | Sprint 2 | TODO | src/services/api.jsx | Add exponential backoff (3 retries, 1s/2s/4s)
ERR-05 | No error state in seedStore | Error Handling | P1 | Sprint 2 | TODO | src/stores/seedStore.jsx | Add error field, propagate to UI
ERR-06 | Missing security event logging | Error Handling | P1 | Sprint 2 | TODO | server.ts | Log WARN for auth failures, deletions, privilege ops
ERR-07 | Asset pipeline silently skips on failure | Error Handling | P2 | Sprint 3 | TODO | src/lib/pipeline/index.ts L79-81 | Return error object, show warning to user
ERR-08 | GSPL parser regex has no error recovery | Error Handling | P2 | Sprint 3 | TODO | src/lib/gspl-parser.ts L54 | Add error messages per regex match failure
DAT-01 | MongoDB never connected — seeds are in-memory | Data Layer | P0 | Sprint 1 | TODO | server.ts | Implement MongoDB driver or document in-memory-only mode
DAT-02 | No database indexes | Data Layer | P1 | Sprint 2 | TODO | N/A | Add indexes on user_id, created_at, domain, hash
DAT-03 | No migration system | Data Layer | P1 | Sprint 2 | TODO | N/A | Add migrate-mongo or manual versioned migrations
DAT-04 | No backup/restore strategy | Data Layer | P2 | Sprint 3 | TODO | N/A | Add mongodump cron job or documented restore procedure
DAT-05 | Seed gallery not persisted on frontend | Data Layer | P2 | Sprint 3 | TODO | src/stores/seedStore.jsx | Add localStorage persistence for gallery state
API-01 | No OpenAPI/Swagger docs | API Completeness | P1 | Sprint 2 | TODO | server.ts | Add swagger-jsdoc + Swagger UI on /api-docs
API-02 | No graceful shutdown handler | API Completeness | P1 | Sprint 2 | TODO | server.ts | Handle SIGTERM/SIGINT, drain connections, save state
API-03 | No API versioning | API Completeness | P2 | Sprint 3 | TODO | server.ts | Prefix all routes with /api/v1/
FE-01 | No auth guards on /studio route | Frontend Polish | P1 | Sprint 1 | TODO | src/App.tsx | Add ProtectedRoute wrapper checking authStore
FE-02 | No token refresh — expired JWT logs out | Frontend Polish | P1 | Sprint 2 | TODO | src/services/api.jsx | Intercept 401, attempt refresh, retry original request
FE-03 | Zero accessibility (0 aria-labels) | Frontend Polish | P1 | Sprint 3 | TODO | All studio components | Add aria-labels, roles, keyboard nav, focus indicators
FE-04 | GSPL editor has no syntax highlighting | Frontend Polish | P2 | Sprint 3 | TODO | src/components/studio/GSPLEditor.jsx | Integrate Monaco or CodeMirror with GSPL grammar
FE-05 | Studio layout breaks at 1024px | Frontend Polish | P2 | Sprint 3 | TODO | App.css L168-177 | Add tablet breakpoint, show collapsible panels
FE-06 | LineageGraph O(n²) per render | Frontend Polish | P2 | Sprint 3 | TODO | src/components/studio/LineageGraph.jsx | Memoize force layout, throttle re-renders
FE-07 | No loading state on initial gallery load | Frontend Polish | P2 | Sprint 3 | TODO | src/pages/StudioPage.jsx L27-31 | Show skeleton/spinner during loadGallery
TST-01 | No API endpoint integration tests | Testing | P1 | Sprint 2 | TODO | tests/ | Add supertest or Vitest tests for all HTTP endpoints
TST-02 | No frontend component tests | Testing | P2 | Sprint 3 | TODO | tests/ | Add React Testing Library tests for studio components
TST-03 | E2E tests not implemented | Testing | P2 | Sprint 3 | TODO | tests/e2e/ | Implement Playwright tests for critical flows
TST-04 | Smoke test expects live server | Testing | P2 | Sprint 3 | TODO | scripts/smoke-test.mjs | Add CI step that starts server before smoke test
OPS-01 | CI deploy steps are stubs (echo only) | DevOps & Deploy | P1 | Sprint 2 | TODO | .github/workflows/ci.yml L209-228 | Fill in real deployment (SSH, Docker push, k8s apply)
OPS-02 | NODE_ENV not enforced in production | DevOps & Deploy | P1 | Sprint 2 | TODO | server.ts L1226 | Throw error if NODE_ENV not set
OPS-03 | No health check differentiation | DevOps & Deploy | P2 | Sprint 3 | TODO | server.ts, Dockerfile | Separate /healthz (simple 200) from /health (stats)
OPS-04 | Dockerfile tsx global install fragile | DevOps & Deploy | P2 | Sprint 3 | TODO | Dockerfile L22 | Copy tsx from build stage or use compiled JS
DOC-01 | README says 26 domains (should be 27) | Documentation | P1 | Sprint 1 | TODO | README.md | Update all references: 27 domains, 12 bridges, 17 gene types
DOC-02 | No deployment guide | Documentation | P2 | Sprint 3 | TODO | N/A | Write DigitalOcean/AWS deployment walkthrough
OBS-01 | No error tracking (Sentry/DataDog) | Observability | P1 | Sprint 2 | TODO | server.ts, frontend | Add Sentry SDK to both backend and React
OBS-02 | No structured audit trail | Observability | P1 | Sprint 2 | TODO | server.ts | Log all mutations, deletions, auth events with user ID + timestamp
OBS-03 | Frontend errors vanish (console only) | Observability | P2 | Sprint 3 | TODO | All components | Wire error boundary + toast errors to Sentry/logging

## Sprint Plan
SPRINT PLAN — 12 → 100 in 6 Weeks
Sprint 1 — Foundation Security (Week 1-2) |  | Score: 12 → 45
☐ | Add Zod validation schemas to all 12 POST/PUT endpoints
☐ | Add cors + helmet middleware to server.ts
☐ | Add pagination (limit/offset) to GET /api/seeds
☐ | Add requireAuth middleware — protect all seed mutations + delete
☐ | Lock down /metrics, WebSocket auth, remove private key from bodies
☐ | Add ErrorBoundary + WebGL fallback + toast errors (sonner) in frontend
☐ | Enforce JWT_SECRET required in production
☐ | Update README: 27 domains, 12 bridges, 211 tests
Sprint 2 — Data & Reliability (Week 3-4) |  | Score: 45 → 72
☐ | Implement MongoDB persistence (connect, CRUD, indexes)
☐ | Add Redis-backed rate limiting + JWT blacklist
☐ | Implement refresh token rotation
☐ | Add role-based access control (admin/user)
☐ | Add API retry logic + exponential backoff in frontend
☐ | Add error state to seedStore, propagate to all components
☐ | Add Sentry error tracking (backend + frontend)
☐ | Add structured audit logging for all mutations
☐ | Fill in CI deploy steps with real Docker push + staging deploy
☐ | Add OpenAPI/Swagger on /api-docs
☐ | Add API endpoint integration tests (supertest)
Sprint 3 — Polish & Hardening (Week 5-6) |  | Score: 72 → 100
☐ | Add CSRF protection (SameSite cookies)
☐ | Nonce-based CSP in nginx (remove unsafe-inline)
☐ | Add MongoDB/Redis auth in docker-compose
☐ | Add graceful shutdown handler (SIGTERM/SIGINT)
☐ | Implement frontend accessibility (aria-labels, keyboard nav, focus)
☐ | Add GSPL syntax highlighting (Monaco/CodeMirror)
☐ | Fix responsive layout for tablet (1024px breakpoint)
☐ | Memoize LineageGraph force layout
☐ | Add frontend component tests (React Testing Library)
☐ | Add Playwright E2E tests for critical flows
☐ | Write deployment guide (DigitalOcean/AWS)
☐ | Add backup/restore documentation
☐ | Final production readiness review